## Lookup
Sheet lookups
Task Status | Note
Active | Work in progress on task
Pending | In queue waiting to start
Paused | Task paused for a reason. Work will restart when cleared to.
Cancelled | task terminated will not restart.
Complete | Task completed

## Template
Notes | Code - Attached to a test to enable sorting on the task list
Task - Name and short description of task
Sheet - link to sheet detailing sub tasks
Status - current status of task
Code | Task | Sheet | Status

## Title
Project | Purchase Order
Project Description | A web based application to enable a user to produce, manage and email Purchase Orders to a recipient.
Status | Under development

## Master
Code | Task | Sheet | Status
M-100 | Create solution and add Projects UI,DataAccess and TestConsole in Visual Studio | M-100'!A1 | Complete
M-200 | Compose the Data access Layer | M-200'!A1 | Complete
M-210 | Compose Repository Project |  | Complete
M-220 | Compose Models project | M-220'!A1 | Complete
M-240 | Compose Services Project | M-240'!A1 | Pending
M-250 | Compose Test Console Project. | M-300'!A1 | Complete
M-400 | Compose UI Project | M400'!A1 | Active

## M-100
Create solution Projects in Visual Studio
Code | Task | Sheet | Status
M-100-A | Create Solution with User Interface(UI) project and apply Individual User Accounts Authentication Option |  | Complete
M-100-B | Modify the database connection string in the appsettings.json file to set the development database name |  | Complete
M-100-C | Create DataAccess project Contains description of the database schema, table models and data access code. |  | Complete
M-100-D | Create Test Console project place test code in the project here |  | Complete
M-100-E | Create Class Library project Service contains services consumed by the solution |  | Complete

## M-200
Compose the Data access Layer
Code | Task | Sheet | Status
M-200-A | Install Entity framework core Nuget Package Microsoft.EntityFrameworkCore |  | Complete
M-200-A-100 | Install Entity framework core Nuget Package Microsoft.AspNetCore.Identity.EntityFrameworkCore |  | Complete
M-200-A-200 | Install Entity framework core Nuget Package Microsoft.EntityFrameworkCore.SqlServer |  | Complete
M-200-A-300 | Move ApplicationDBContext from UI project to DataAccess project |  | Complete
M-200-A-400 | Delete Folder UI.Data |  | Complete
M-200-B | Compose entity Database table models |  | Complete
M-200-C | Use migrations to create the database Note remember to change IdentityUser to ApplicationUser in the UI startup class |  | Complete
M-200-D | Create Repository / Unit of work class |  | Complete

## M-220
Compose Models project
Code | Task | Sheet | Status
| Generate Models |  | Complete
| Compose DTO methods for use |  | Complete

## M-240
Compose Services Project
Code | Task | Sheet | Status
M-240-100

## M-300
In Test Console Compose and add tests to check opperations in the Data Access layer.
Code | Task | Sheet | Status
M-300a | Compose funtionality checks on objects built into system |  | Active

## M400
Compose UI Project
Code | Task | Sheet | Status
M400-100 | Scafold out Identity |  | Complete
M400-200 | Modify views to display and save the additional User details |  | Complete
M400-300 | Test Register and Modify User details in the app |  | Complete
M400-400 | Build app views | M400-400'!A1 | Paused
M400-500 | Set up microsoft App secrets in the UI project | M400-500'!A1 | Complete
M400-600 | Setup email service | M400-600'!A1 | Complete

## M400-400
Build app views
Code | Task | Sheet | Status
M400-400-100 | Compose PO ViewModel |  | Complete
M400-400-200 | Compose PO PO ViewModel \ Table Models Data transfer Object |  | Complete
M400-400-300 | Compose PO View Controller |  | Complete
M400-400-400 | Compose PO Index View |  | Complete
M400-400-500 | Compose PO Raise\Edit PO View |  | Complete
M400-400-600 | Modify Purchase Order repository to do Paging ie set No of lines per page |  | Paused | Going to do this after publishing system on Azure
M400-400-700 | Compose Organisation Controller and Index , Create, Edit, delete Views |  | Complete
M400-400-800 | Compose Organisation Items Controller and Index , Create, Edit, delete Views |  | Complete
M400-500-900 | Compose view to alter status of PO |  | Complete

## M400-500
Set up microsoft App secrets in the UI project
Code | Task | Sheet | Status
| Install Microsoft.Extensions.Configuration.UserSecrets nuget package |  | Complete
Add Sendgrid app key to the secrets.json file

## M400-600
Setup sendgrid email service
Code | Task | Sheet | Status
M400-600-100 | Install Sendgrid nuget package into the UI project |  | Complete
M400-600-200 | In Startup.cs setup the application secrets |  | Complete
M400-600-300 | Test sending of emails |  | Complete